## Sheet1
Project | Haptic Feedback Glove (Originial) | [29 empty] | Key | Hardware
Student | Benjamin Wickenden 10557913 | [30 empty] | Software
Project Supervisor | David Jenkins | [30 empty] | Research
2nd Project Supervisor | [31 empty] | Deadline
Project Manager | Paul Davey | [30 empty] | Meetings
| Haptic Feedback Glove Project: Benjamin Wickenden 10557913 | October |  |  |  | November |  |  |  | December |  |  |  |  | January |  |  |  | Febuary |  |  |  | March |  |  |  | April |  |  |  |  | May
| Date(Week Beginning) | 8th | 15th | 22nd | 29th | 5th | 12th | 19th | 26th | 3rd | 10th | 17th | 24th | 31st | 7th | 14th | 21st | 28th | 4th | 11th | 18th | 25th | 4th | 11th | 18th | 25th | 1st | 8th | 15th | 22nd | 29th | 6th | 13th | 20th
Tasks:
Stage 1: Preliminary Research | Research into project ideas | bar: October 8th to October 15th
Initial Proposal 15th October | bar: October 15th
Research into Haptics | bar: October 8th to December 31st
Final Proposal 31st October | bar: October 29th
Stage 2: Research | Research Unity Simulations | bar: October 8th to November 26th
Research How to send Data from Unity to Arduino | bar: October 29th to November 12th
Research Rumble Motors | bar: November 5th to November 26th
Research Shape Memory Alloys | bar: October 29th to December 31st
Stage 3: Design and Prototype | Create a Simulation in Unity | bar: November 19th to January 21st
Develop code to communicate between Unity and Arduino | bar: December 3rd to January 21st
Test Arduino code | bar: January 7th to January 28th
Create a shield for the Arduino | bar: March 4th to March 11th
Test Shape Memory Alloys | bar: November 19th to January 28th
Create a Prototype Shape Memory Alloy spring | bar: January 28th to Febuary 25th
Design a Prototype Glove and Rig | bar: Febuary 11th to Febuary 25th
Develop Arduino code to control Shape Memory Alloy Springs and Rumble Motors | bar: Febuary 11th to Febuary 25th
Construct Prototype Glove | bar: March 4th to March 11th
Test Prototype Glove | bar: March 4th to March 11th
Stage 4: Improvement and Final Product | Improve Protoype | bar: March 18th to March 25th
Impliment improvements to Glove | bar: April 1st to April 22nd
Test Final Glove | bar: April 29th to May 6th
Stage 5: Deadlines | Project Progress Demo 15th March | bar: March 11th
Project Vivas 15th May | bar: May 13th
Project Showcase 16th May | bar: May 13th
Project Report 4pm 20th May | bar: May 20th
Meetings | Project Supervisor Meetings | bar: October 8th; October 22nd; November 5th; November 19th; December 3rd; January 14th; January 28th to May 6th
Meetings
Notes